## Slide 1
USE CASE PULSE · CATENA-X
Overview
7 use cases · sorted by overall status
Status legend
On Track
Problem Solving
Escalation needed
Not Started
Completed
Date
CW 40 / 2026
USE CASE
OVERALL STATUS
PHASE
NEXT MILESTONE
DIMENSIONS
SUPPLIERS ENABLED 2026
Quality
quality-cx
Escalation needed
Piloting
Domain expertise aligned
30 Sep 2026
External · CX Association
Business
Data Provisioning
Technical
Supplier Activation
0 / 1 0% · rescoped
1
Battery Passport
Batt Pass
Problem Solving
Pilot
Tech requirements done
31 Oct 2026
External · CX Association
Business
Data Provisioning
Technical
Supplier Activation
0 / 1 0%
–
Product Passes
pass-cx
Problem Solving
Definition
Klärung & Prio Produktpässe
31 Oct 2026
External · CX Association
Business
Data Provisioning
Technical
Supplier Activation
0 / 1 0%
–
PURIS
PURIS
Problem Solving
Piloting
Plan for existing challenges
9 Oct 2026
External · CX Association
Business
Data Provisioning
Technical
Supplier Activation
1 / 6 17%
2
Business Partner Data Mgmt
BPDM
Problem Solving
Implementation
Define BPDM target picture
31 Oct 2026
External · CX Association
Business
Data Provisioning
Technical
Supplier Activation · not started
0 / 1 0%
–
Certificate Management
cert-mgmt
Problem Solving
Scaling
Official CX CCM release
Sep 2026
External · CX Association
Business
Data Provisioning
Technical
Supplier Activation
72 / 100 72%
–
Product Carbon Footprint
pcf-cx
On Track
Piloting
Supplier activation pilot 1
15 Oct 2026
External · CX Association
Business
Data Provisioning
Technical
Supplier Activation
0 / 1 0%
–
Decisions required:
1
Quality: Approve rescoping from 15 to 1 supplier until the Early Warning Production MVP is live?
2
PURIS: When and how should the WINGS connectivity rollout roadmap be decided?
Notes: Use Case Pulse Overview CW 40 / 2026 – one row per use case, sorted by overall status.