## Slide 1
USE CASE PULSE · CATENA-X
Management Overview
Management report on the status of all Catena-X use cases
Status legend
On Track
Problem Solving
Escalation needed
Not Started
Completed
Date
CW 40 / 2026
Quality
quality-cx
Battery Passport
battpass-cx
Product Passes
pass-cx
PURIS
puris-cx
Business Partner Data Mgmt
bpdm-cx
Certificate Management
cert-mgmt
Product Carbon Footprint
pcf-cx
Overall status
Escalation needed
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
On Track
Phase
Piloting
Pilot
Definition
Piloting
Implementation
Scaling
Piloting
Next milestone
Domain expertise aligned
30 Sep 2026
Tech requirements done
31 Oct 2026
Klärung & Prio Produktpässe
31 Oct 2026
Plan for existing challenges
9 Oct 2026
Define BPDM target picture
31 Oct 2026
Official CX CCM release
Sep 2026
Supplier activation pilot 1
15 Oct 2026
Dimensions
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
Suppliers enabled 2026
0 / 1 0%
rescoped from 15
0 / 1 0%
0 / 1 0%
1 / 6 17%
0 / 1 0%
72 / 100 72%
0 / 1 0%
Goal: E2E go-live target
MVP Jan '27
Scaling until 2030
Feb 2027
– not defined yet
– not specified
Feb 2027
May 2028
01 Jan 2028
Decision required
1
Approve rescoping from 15 to 1 supplier until the Early Warning Production MVP is live?
–
–
2
When and how should the WINGS connectivity rollout roadmap be decided?
–
–
–
Notes: Use Case Pulse Management Overview CW 40 / 2026 – one column per use case (read top to bottom), one KPI per row, sorted by overall status.