## Slide 1
USE CASE PULSE · CATENA-X
Management Overview of Use Cases
Status as of
CW 41 / 2026
On Track
Problem Solving
Escalation needed
Not Started
Quality
quality-cx
Kutritz (K-GQY)
Battery Passport
batt-cx
Alp (ZG-R)
Product Passes
pass-cx
Drobir (K-GEP-2)
PURIS
puris-cx
Timpe (KL-GP), Behrens (BZ-PX)
Business Partner Data Mgmt
bpdm-cx
Fehlner (I/BZ)
Certificate Management
cert-cx
Poetsch (K-DDX/5)
Product Carbon Footprint
pcf-cx
Dettmer (K-GEN), Voeste (K-GSS)
N-Tier
ntier-cx
Fink (BZI2)
Name
Domain Lead
Overall status
Escalation needed
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
On Track
On Track
Phase
Piloting
Piloting
Definition & Clarification
Piloting
Implementation
Scaling
Piloting
Definition & Clarification
E2E go-live target date
MVP Jan '27
Scaling until 2030
Feb 2027
– not defined yet
– not defined yet
Feb 2027
May 2028
01 Jan 2028
– not defined yet
Suppliers enabled 2026
0 / 2 0%
rescoped from 15
0 / 1 0%
0 / 1 0%
1 / 6 17%
0 / 1 0%
82 / 100 82%
0 / 1 0%
N/A
Next critical milestone
SQA CX MVP scale-up
31 Jan 2027
No critical milestone
Product passes prioritized
31 Oct 2026
Plan for existing challenges ready
9 Oct 2026
No critical milestone
Official CX CCM release
Sep 2026
No critical milestone
No critical milestone
Dimensions
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
Decision required
1
Approve rescoping from 15 to 2 suppliers until the Early Warning Production MVP is live?
–
–
2
Who decides how and when on the WINGS connectivity rollout roadmap?
–
–
–
–
Notes: Use Case Pulse Management Overview CW 41 / 2026 – one card per use case (read top to bottom), sorted by overall status. Next critical milestone = most critical amber/red milestone.

## Slide 2
ENABLING PULSE · CATENA-X
Management Overview of Enabling Streams
Status as of
CW 41 / 2026
On Track
Problem Solving
Escalation needed
Not Started
Supplier Activation
sac-cx
Behrens (BZ-PX)
Portfolio, AI+, C-X NEXT, DigiTrace
port-cx
Bollmann, Poetsch (K-DDX/5)
Data Provisioning
dpr-cx
Bollmann, Poetsch (K-DDX/5)
Hub & Spoke
hub-cx
Bollmann, Poetsch (K-DDX/5)
Legal & Contracts
gis-cx
Pietschmann
Architecture
arch-cx
tbd
Name
Domain Lead
Overall status
Escalation needed
Escalation needed
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Goal
All P-Mat suppliers operationally connected
Budget and funding secured in every planning round
Catena-X data provided as shoppable data products
Catena-X scaled across all brands via Hub & Spoke
Framework contracts with brands and data consumers in place
Approved, scalable Catena-X target architecture
Key KPI actual / target
Suppliers contracted by Q3
240 / 280
PR74 & PR75 secured
tbd / 2 by 31 Dec 2026
Use Case Owners approved
6 / 8
Brands signed
8 / 17
Automated contract cycle live
tbd / 01 Jan 2028
– not defined yet
Suppliers enabled 2026
240 / 400 55%
228 company groups
–
–
–
–
–
Next critical milestone
280 suppliers contracted
30 Sep 2026
Secure PR74
Nov 2026
No critical milestone
Framework agreements signed
31 Dec 2026
Managed by Cofinity-X
Oct 2026
No critical milestone
Dimensions
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
Decision required
1
Red: Cofinity-X processes and portal unclear for suppliers; DSA confirmation costs per use case open
2
PR75: which costs are planned per use case?
3
New PR75 process: capacity crunch & high risks?
4
DigiTrace: stop, or fund for 2027?
–
–
–
–