## Slide 1
CATENA-X
Management Overview of Use Cases
Status as of
CW 42 / 2026
On Track
Problem Solving
Escalation needed
Not Started
Quality
quality-cx
Kutritz (K-GQY)
Battery Passport
batt-cx
Alp (ZG-R)
Product Passes
pass-cx
Drobir (K-GEP-2)
PURIS
puris-cx
Timpe (KL-GP), Behrens (BZ-PX)
Business Partner Data Mgmt
bpdm-cx
Fehlner (I/BZ)
Certificate Management
cert-cx
Poetsch (K-DDX/5)
Product Carbon Footprint
pcf-cx
Dettmer (K-GEN), Voeste (K-GSS)
N-Tier
ntier-cx
Fink (BZI2)
Name
Domain Lead
Overall status
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
On Track
Phase
Piloting
Piloting
Definition & Clarification
Piloting
Implementation
Scaling
Piloting
Definition & Clarification
E2E go-live target date
MVP Jan 2027
Scaling until 2030
Feb 2027
– not defined yet
– not defined yet
Feb 2027
May 2028
Jan 2028
– not defined yet
Suppliers enabled 2026
0 / 2 0%
rescoped from 15
0 / 1 0%
0 / 1 0%
1 / 6 17%
0 / 1 0%
89 / 100 89%
0 / 1 0%
N/A
Next critical milestone
Domain expertise & ownership aligned
30 Sep 2026
No critical milestone
Product passes prioritized
31 Oct 2026
Plan for existing challenges ready
09 Oct 2026
No critical milestone
Official CX CCM release
Sep 2026
Supplier activation pilot stage 1
15 Oct 2026
No critical milestone
Dimensions
CX Association
Business
Data Provisioning
Technical
Supplier Activation
Decision required
–
–
–
1
Who decides how and when on the WINGS connectivity rollout roadmap?
–
–
–
–
Notes: Use Case Pulse Management Overview CW 42 / 2026 – one card per use case (read top to bottom), sorted by overall status. Next critical milestone = most critical amber/red milestone.