## Slide 1
CATENA-X
Management Overview of Use Cases
Status as of
CW 42 / 2026
On Track
Problem Solving
Escalation needed
Not Started
Quality
quality-cx
Kutritz (K-GQY)
Battery Passport
batt-cx
Alp (ZG-R)
Product Passes
pass-cx
Drobir (K-GEP-2)
PURIS
puris-cx
Timpe (KL-GP), Behrens (BZ-PX)
Business Partner Data Mgmt
bpdm-cx
Fehlner (I/BZ)
Certificate Management
cert-cx
Poetsch (K-DDX/5)
Product Carbon Footprint
pcf-cx
Dettmer (K-GEN), Voeste (K-GSS)
N-Tier
ntier-cx
Fink (BZI2)
Name
Domain Lead
Overall status
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
On Track
Phase
Piloting
Piloting
Definition & Clarification
Piloting
Implementation
Scaling
Piloting
Definition & Clarification
E2E go-live target date
MVP Jan 2027
Scaling until 2030
Feb 2027
– not defined yet
– not defined yet
Feb 2027
May 2028
Jan 2028
– not defined yet
Suppliers enabled 2026
0 / 2 0%
rescoped from 15
0 / 1 0%
0 / 1 0%
1 / 6 17%
0 / 1 0%
89 / 100 89%
0 / 1 0%
N/A
Next critical milestone
Domain expertise & ownership aligned
30 Sep 2026
No critical milestone
Product passes prioritized
31 Oct 2026
Plan for existing challenges ready
09 Oct 2026
No critical milestone
Official CX CCM release
Sep 2026
Supplier activation pilot stage 1
15 Oct 2026
No critical milestone
Dimensions
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
External ·
CX Association
Business
Data Provisioning
Technical
Supplier Activation
Decision required
–
–
–
1
Who decides how and when on the WINGS connectivity rollout roadmap?
–
–
–
–
Notes: Use Case Pulse Management Overview CW 42 / 2026 – one card per use case (read top to bottom), sorted by overall status. Next critical milestone = most critical amber/red milestone.

## Slide 2
CATENA-X
Management Overview of Enabling Streams
Status as of
CW 42 / 2026
On Track
Problem Solving
Escalation needed
Not Started
Portfolio, AI+, C-X NEXT, DigiTrace
port-cx
Kraus (K-DDX/5)
Supplier Activation
sac-cx
Stuhrmann (BZ-PX)
Data Provisioning
dpr-cx
Kraus (K-DDX/5)
Hub & Spoke
hub-cx
Kraus (K-DDX/5)
Legal & Contracts
gis-cx
Brunke (K-ILX-6), Schiffelbaum (A-IIED-EJ)
Architecture
arch-cx
Fischer (K-DCC/B)
Name
Workstream Lead
Overall status
Escalation needed
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Goal
Budget and funding secured in every planning round
All P-Mat suppliers operationally connected
Catena-X data provided as shoppable data products
Catena-X scaled across all brands via Hub & Spoke
Framework contracts with all brands and data consumers
Approved, scalable Catena-X target architecture
Key KPI
actual / target
Budgets secured
0 / 2 (PR74, PR75)
Suppliers contracted by Q3
240 / 280
Use Case Owners approved
6 / 8
Brands signed
8 / 17
Automated contract cycle
not live / live by 01 Jan 2028
– not defined yet
Next critical milestone
Secure PR75
31 Oct 2026
EoY goal: 400 suppliers contracted
31 Dec 2026
No critical milestone
Framework agreements signed
31 Dec 2026
Managed by Cofinity-X
Oct 2026
No critical milestone
Dimensions
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
Decision required
1
PR75: which costs are planned per use case?
2
New PR75 process: capacity crunch & high risks?
3
DigiTrace: stop, or fund for 2027?
–
–
–
–
–