## Slide 1
CATENA-X
Management Overview of Enabling Streams
Status as of
CW 41 / 2026
On Track
Problem Solving
Escalation needed
Not Started
Supplier Activation
sac-cx
Stuhrmann (BZ-PX)
Portfolio, AI+, C-X NEXT, DigiTrace
port-cx
Kraus (K-DDX/5)
Data Provisioning
dpr-cx
Kraus (K-DDX/5)
Hub & Spoke
hub-cx
Kraus (K-DDX/5)
Legal & Contracts
gis-cx
Brunke (K-ILX-6), Schiffelbaum (A-IIED-EJ)
Architecture
arch-cx
Fischer (K-DCC/B)
Name
Workstream Lead
Overall status
Escalation needed
Escalation needed
Problem Solving
Problem Solving
Problem Solving
Problem Solving
Goal
All P-Mat suppliers operationally connected
Budget and funding secured in every planning round
Catena-X data provided as shoppable data products
Catena-X scaled across all brands via Hub & Spoke
Framework contracts with all brands and data consumers
Approved, scalable Catena-X target architecture
Key KPI
actual / target
Suppliers contracted by Q3
240 / 280
Budgets secured
0 / 2 (PR74, PR75)
Use Case Owners approved
6 / 8
Brands signed
8 / 17
Automated contract cycle
not live / live by 01 Jan 2028
– not defined yet
Next critical milestone
280 suppliers contracted
30 Sep 2026
Secure PR74
Nov 2026
No critical milestone
Framework agreements signed
31 Dec 2026
Managed by Cofinity-X
Oct 2026
No critical milestone
Dimensions
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
External ·
CX Association
Business
Use Cases
Technical
Decision required
1
How do we make Cofinity-X onboarding clear for suppliers, and who covers the data sharing agreement (DSA) costs per use case?
2
PR75: which costs are planned per use case?
3
New PR75 process: capacity crunch & high risks?
4
DigiTrace: stop, or fund for 2027?
–
–
–
–
Notes: Enabling Pulse Management Overview CW 41 / 2026 – one card per enabling stream (read top to bottom), sorted by overall status. Next critical milestone = most critical amber/red milestone.